## Gantt chart
HomeGrow
|  | Project Start: | 2022-05-03
|  | Today: | 2022-07-01
|  | Display Week: | 1 |  |  | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23 | [6 empty] | 2022-05-30 | [6 empty] | 2022-06-06 |  |  |  |  | 2022-06-11 | [6 empty] | 2022-06-18 | [6 empty] | 2022-06-25 | [6 empty] | 2022-07-02 | [6 empty] | 2022-07-09 | [6 empty] | 2022-07-16
 | time axis 2022-05-02 to 2022-07-20
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
General
1: Set up meeting with client and supervisor | Everyone
1.1: Briefing of project by client |  | 100% | 2022-05-03 | 2022-05-06 | 4
1.2: Briefing of project to supervisor |  | 100% | 2022-05-04 | 2022-05-06 | 3
2: Research technologies | Everyone
2.1: Research current systems and technology |  | 100% | 2022-05-09 | 2022-05-13 | 5
3: Design basic system layout | Everyone
3.1: Design hardware frame |  | 100% | 2022-05-16 | 2022-05-20 | 5
3.2: Establish technology stack |  | 100% | 2022-05-16 | 2022-05-20 | 5
3.4: Discuss with client about implementation idea |  | 100% | 2022-05-19 | 2022-05-20 | 5
4: Design leaflet
4.1: Research competitors and business models | Batuhan Cinar | 100% | 2022-05-23 | 2022-05-25 | 3
4.2: Writing up marketing content | Everyone | 100% | 2022-05-23 | 2022-05-25 | 3
4.4: Designing layout | Kaling Ng | 100% | 2022-05-26 | 2022-05-26 | 1
4.5: Present leaflet to supervisor and client | Everyone | 100% | 2022-05-27 | 2022-05-27 | 1
5: Sourcing materials
5.1: Creating bill-of-materials | Jing Lin Loh, Timothy Moores | 100% | 2022-05-23 | 2022-05-24 | 2
5.2: Placing orders | Jing Lin Loh | 100% | 2022-05-25 | 2022-05-25 | 1
6: Design poster
6.1: Create A1 poster for hackbooth presentation | Everyone | 100% | 2022-06-20 | 2022-06-22 | 3
Hardware
1: Setting up hardware frame | Batuhan Cinar, Yash Rajput, Kaling Ng
1.1: Cutting UPVC Pipes |  | 100% | 2022-05-30 | 2022-05-31 | 2
1.2: Connecting pipes and joints |  | 100% | 2022-06-01 | 2022-06-02 | 2
1.3: Drilling holes in reservoir |  | 100% | 2022-06-03 | 2022-06-03 | 1
2: Setting up Raspberry Pi and sensors | Yash Rajput, Jing Lin Loh, Timothy Moores
2.1: Programming sensors |  | 100% | 2021-06-04 | 2021-06-08 | 5
2.2: Setting up GPIO connections |  | 100% | 2022-06-09 | 2022-06-11 | 3 | bar: 2022-06-09 to 2022-06-10; 2022-07-19 to 2022-07-20
3: Setting up voltage circuit | Yash Rajput | 100% | 2022-06-15 | 2022-06-20 | 6
Database
Research | Timothy Moores | 100% | 2022-05-30 | 2022-06-02 | 4
Set up Amnesia database | Timothy Moores | 100% | 2022-06-03 | 2022-06-10 | 8
Integrate with voice recognition system | Timothy Moores | 100% | 2022-06-14 | 2022-06-17 | 4
Integrate with front end | Timothy Moores | 100% | 2022-06-18 | 2022-06-22 | 5
Frontend
Research | Benjamin Tan | 100% | 2022-05-30 | 2022-06-02 | 4
Create a node-red app instance | Benjamin Tan | 100% | 2022-06-03 | 2022-06-05 | 2 | bar: 2022-05-02 to 2022-06-05; 2022-06-11 to 2022-07-15
Deploy node-red instance | Benjamin Tan | 100% | 2022-06-06 | 2022-06-09 | 3
Enables custom type inputs | Benjamin Tan | 100% | 2022-06-10 | 2022-06-14 | 4
Style the different display nodes | Benjamin Tan | 100% | 2022-06-15 | 2022-06-17 | 2 | bar: 2022-05-02 to 2022-06-05; 2022-06-11 to 2022-07-15
Setup connection to the database | Benjamin Tan | 100% | 2022-06-18 | 2022-06-25 | 7
Voice Recognition
1: Research | Jing Lin Loh, Kaling Ng
1.1: Research technology stack |  | 100% | 2022-05-30 | 2022-06-02 | 4
2: Implement architecture on Node-RED | Jing Lin Loh, Kaling Ng
2.1: Setting up instances on IBM Cloud |  | 100% | 2022-06-02 | 2022-06-03 | 2
2.2: Adding nodes onto Node-RED |  | 100% | 2022-06-06 | 2022-06-06 | 1
2.3: Setting up Watson Assistant |  | 100% | 2022-06-07 | 2022-06-08 | 2 | bar: 2022-06-08; 2022-07-18
2.4: Training Watson Assistant |  | 100% | 2022-06-09 | 2022-06-13 | 5 | bar: 2022-06-09 to 2022-06-10; 2022-07-19 to 2022-07-20
2.5: Connecting with database on Node-RED |  | 100% | 2022-06-14 | 2022-06-17 | 4
2.6: Integrating with frontend |  | 100% | 2022-06-18 | 2022-06-22 | 5
Integration
Integrate circuit with hardware frame | Batuhan Cinar, Yash Rajput | 100% | 2022-06-21 | 2022-06-21 | 1
Integrate sensors with database through MQTT | Jing Lin Loh, Timothy Moores | 100% | 2022-06-21 | 2022-06-21 | 1
Integrate database with frontend | Timothy Moores, Benjamin Tan | 100% | 2022-06-18 | 2022-06-22 | 5
Integrate voice assistant with frontend | Jing Lin Loh, Kaling Ng, Benjamin Tan | 100% | 2022-06-18 | 2022-06-22 | 5
Test for MQTT connection | Jing Lin Loh, Benjamin Tan, Timothy Moores | 100% | 2022-06-23 | 2022-06-23 | 1
Test for frontend <-> backend | Benjamin Tan, Timothy Moores | 100% | 2022-06-24 | 2022-06-25 | 2
Test entire system | Everyone | 100% | 2022-06-26 | 2022-06-28 | 3
Note on G6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.